## Product Backlog
MoSCoW ID | Product Backlog ID | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk / Impact (L-Low, M-Medium, H-High) | Type | Comments
1 | 1 | M |  | User must register themselves | Simple | M | Functional
2 | 2 | S |  | User must login to the application | Simple | H | Functional
3 | 3 | M |  | User can view doctor's details | Average | M | Functional
4 | 4 | S |  | User can book an appointment | Complex | M | Technical
5 | 5 | S |  | User can see appointment history | Average | L | Functional
6 | 6 | S |  | User can login incase they forget password | Average | M | Technical
7 | 7 | W |  | User can't delete account | Simple | M | Non-functional
8 | 8 | C |  | User can cancel/reschedule appointments | Complex | H | Technical
9 | 9 | M |  | Admin can login | Simple | M | Functional
10 | 10 | C |  | Admin can view patient's details/list | Average | M | Functional
11 | 11 | C |  | Admin can view doctor's details/list | Simple | M | Functional
12 | 12 | M |  | Admin can reschedule/accept/cancel appointments | Complex | H | Technical
13 | 13 | W |  | Payments can't be accepted | Complex | M | Non-functional
14 | 14 | M |  | User get the notification for their appointment | Complex | H | Functional
15 | 15 | W |  | User can generate an appointment / billsummary | Complex | M | Technical
16 | 16 | S |  | User can update mobile number | Average | M | Technical
17 | 17 | M |  | User can logout | Simple | L | Functional
18 | 18 | M |  | Admin can logout | Simple | L | Functional
19 | 19 | C |  | Admin can update doctor's list | Average | H | Technical
20 | 20 | C |  | Admin can update doctor details | Average | H | Technical
21 | 21 | W |  | Third party applications are not supported yet | Average | M | Non-functional
22 | 22 | S |  | User can update password | Average | M | Technical
23 | 23 | W |  | User can get the token number | Complex | H | Non-functional

## Sprint Backlog
Product Backlog ID | User Story ID | User Story Task Step number | Task Step Description | Assigned to | Assigned Date | Original Estimantion | Adjusted Estimation | Status | Actual Efforts