## Product Backlog
MoSCoW ID | Product Backlog ID | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk / Impact (L-Low, M-Medium, H-High) | Type | Comments
1 | 1 | M |  | User must register themselves | Simple | M | Functional
2 | 2 | S |  | User must login to the application | Simple | H | Functional
3 | 3 | M |  | User can view doctor's details | Average | M | Functional
4 | 4 | S |  | User can book an appointment | Complex | M | Technical
5 | 5 | S |  | User can see appointment history | Average | L | Functional
6 | 6 | S |  | User can login incase they forget password | Average | M | Technical
7 | 7 | W |  | User can't delete account | Simple | M | Non-functional
8 | 8 | C |  | User can cancel/reschedule appointments | Complex | H | Technical
9 | 9 | M |  | Admin can login | Simple | M | Functional
10 | 10 | C |  | Admin can view patient's details/list | Average | M | Functional
11 | 11 | C |  | Admin can view doctor's details/list | Simple | M | Functional
12 | 12 | M |  | Admin can reschedule/accept/cancel appointments | Complex | H | Technical
13 | 13 | W |  | Payments can't be accepted | Complex | M | Non-functional
14 | 14 | M |  | User get the notification for their appointment | Complex | H | Functional
15 | 15 | W |  | User can generate an appointment / billsummary | Complex | M | Technical
16 | 16 | S |  | User can update mobile number | Average | M | Technical
17 | 17 | M |  | User can logout | Simple | L | Functional
18 | 18 | M |  | Admin can logout | Simple | L | Functional
19 | 19 | C |  | Admin can update doctor's list | Average | H | Technical
20 | 20 | C |  | Admin can update doctor details | Average | H | Technical
21 | 21 | W |  | Third party applications are not supported yet | Average | M | Non-functional
22 | 22 | S |  | User can update password | Average | M | Technical
23 | 23 | W |  | User can get the token number | Complex | H | Non-functional
24 | 24

## Sprint Backlog
Product Backlog ID | User Story ID | User Story Task Step number | Task Step Description | Assigned to | Assigned Date | Original Estimantion | Adjusted Estimation | Status | Actual Efforts
P:01 | US:101 | 1 | Create the ER diagram | Team | 2022-10-06 | 2022-10-06 | 2022-10-06 | Done
P:02 | US:102 | 2 | Create the schema diagram | Team | 2022-10-06 | 2022-10-06 | 2022-10-06 | Done
P:03 | US:103 | 3 | Create the application flow | Team | 2022-10-07 | 2022-10-07 | 2022-10-07 | Done
P:04 | US:104 | 4 | Create the database in MySql | Team | 2022-10-10 | 2022-10-10 | 2022-10-10 | Done
P:05 | US:105 | 5 | Create the Spring Starter project | Team | 2022-10-10 | 2022-10-10 | 2022-10-10 | Done
P:06 | US:106 | 6 | Create Entity/POJO class of Admin | Team | 2022-10-10 | 2022-10-10 | 2022-10-10 | Done
P:07 | US:107 | 7 | Create Entity/POJO class of Appointment | Team | 2022-10-11 | 2022-10-11 | 2022-10-11 | Done
P:08 | US:108 | 8 | Create Entity/POJO class of Doctor | Team | 2022-10-12 | 2022-10-12 | 2022-10-12 | Done
P:09 | US:109 | 9 | Create Entity/POJO class of Login | Team | 2022-10-13 | 2022-10-13 | 2022-10-13 | Done
P:10 | US:110 | 10 | Create Entity/POJO class of Patient | Team | 2022-10-14 | 2022-10-14 | 2022-10-14 | Done
P:11 | US:111 | 11 | Create package "repository" and interfaces for Admin, Appointment, patient, Login | Team | 2022-10-17 | 2022-10-17 | 2022-10-17 | Done
P:12 | US:112 | 12 | create package "exception" for ResourceNotFoundException handling | Team | 2022-10-18 | 2022-10-18 | 2022-10-18 | Done
P:13 | US:113 | 13 | Create package "service" and classes, interfaces for Admin, Appointment, patient, Login | Team | 2022-10-19 | 2022-10-19 | 2022-10-19 | Done
P:14 | US:114 | 14 | Create package "controller" and classes for Admin, Appointment, patient, Login | Team | 2022-10-20 | 2022-10-20 | 2022-10-20 | Done
P:15 | US:115 | 15 | Implement the swagger | Team | 2022-10-21 | 2022-10-21 | 2022-10-21 | Done
P:16 | US:116 | 16 | Create Custom query to search Doctor by specialization | Team | 2022-10-24 | 2022-10-24 | 2022-10-24 | Done
P:17 | US:117 | 17 | Create wireframes for the front-end | Team | 2022-10-25 | 2022-10-25 | 2022-10-25 | Done
P:18 | US:118 | 18 | Create Patient components folder for CRUD Patient files | Prathyusha | 2022-10-26 | 2022-10-26 | 2022-10-26 | Done
P:19 | US:119 | 19 | Create Appointment components folder for CRUD Appointment files | Trishna | 2022-10-27 | 2022-10-27 | 2022-10-27 | Done
P:20 | US:120 | 20 | Create Doctor components folder for CRUD Doctor files | Tenzing | 2022-10-28 | 2022-10-28 | 2022-10-28 | Done
P:21 | US:121 | 21 | Create frontend components folder for Aboutus,Contactus,Header,Home,HomeAfterLogin,NavBar,Service files | Team | 2022-10-31 | 2022-10-31 | 2022-10-31 | Done
P:22 | US:122 | 22 | Create folder for storing images | Team | 2022-11-01 | 2022-11-01 | 2022-11-01 | Done
P:23 | US:123 | 23 | Create services folder for AdminService,AppointmentService,DoctorService,PatientService | Team | 2022-11-02 | 2022-11-02 | 2022-11-02 | Done
P:24 | US:124 | 24 | Create AdminHomePage JS file | Prathyusha | 2022-11-03 | 2022-11-03 | 2022-11-03 | Done
P:25 | US:125 | 25 | Create MainHeader Jsfile | Prathyusha | 2022-11-04 | 2022-11-04 | 2022-11-04 | Done
P:26 | US:126 | 26 | CreateNavAfterLoginUser JS file | Prathyusha | 2022-11-07 | 2022-11-07 | 2022-11-07 | Done
P:27 | US:127 | 27 | Create TopServices,.dermatologydoc , generaldoc, gynaecologydoc,appointment JS files | Trishna | 2022-11-08 | 2022-11-08 | 2022-11-08 | Done
P:28 | US:128 | 28 | Create SigninAdmin and SigninValidation | Prathyusha | 2022-10-09 | 2022-10-09 | 2022-10-09 | Done
P:29 | US:129 | 29 | Create CSS folder for storing the CSS files | Team | 2022-10-09 | 2022-10-09 | 2022-10-09
30